## RO_0
|  |  |  | 123095.7041 | 139144.8435 | 223303.8495 | 464640.5099 | 219963.0931 | 1170148 | 103.9%
Concept | Current Month (To go-1) | Current Month Real | Cumulative to date | To go Month 1 | To go Month 2 | To go Month 3 | To go Month 4 | To go Month 5 | Current Remaining | At completion Current | At completion Previous | At completion Target
EARN REVENUE |  |  |  | 132677.44 | 149975.84 | 240685.76 | 500808 | 237084.96 | 1261232 | 1261232 |  | 1261232
Earn value Plus work in progrees |  |  |  | 118462 | 133907 | 214898 | 447150 | 211683 | 1126100 | 1126100 |  | 1126100
Profit + overheads (12%) |  |  |  | 14215.44 | 16068.84 | 25787.76 | 53658 | 25401.96 | 135132 | 135132 |  | 135132
Additional Claims | [8 empty] | 0 | 0 |  | 0
Claims to other projects | [8 empty] | 0 | 0 |  | 0
Claims to third parties | [8 empty] | 0 | 0 |  | 0
Claims to subcontractos | [8 empty] | 0 | 0 |  | 0
COST |  |  |  | 131095.7041 | 147144.8435 | 231303.8495 | 472640.5099 | 227963.0931 | 1210148 | 1210148 |  | 1210148 | [5 empty] | 1210148
Materials |  |  |  | 98476.5633 | 41743.453 | 89321.5398 | 185856.204 | 87985.2372 | 503382.9973 | 503382.9973 |  | 503382.9973 | 0.8 | 0.3 | 0.4 | 0.4 | 0.4 | 1170148
Labor |  |  |  | 0 | 83486.9061 | 111651.9247 | 232320.255 | 109981.5465 | 537440.6323 | 537440.6323 |  | 537440.6323 |  | 0.6 | 0.5 | 0.5 | 0.5
Subcontractor |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Plant |  |  |  | 24619.1408 | 13914.4843 | 22330.3849 | 46464.051 | 21996.3093 | 129324.3704 | 129324.3704 |  | 129324.3704 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1
Overhead and indirects |  |  |  | 8000 | 8000 | 8000 | 8000 | 8000 | 40000 | 40000 |  | 40000
[9 empty] | 0 | 0 |  | 0
Margen ('Earn revenue - Cost) |  |  |  | 1581.7359 | 2830.9965 | 9381.9105 | 28167.4901 | 9121.8669 | 51084 | 51084 |  | 51084 | [5 empty] | 51084
%Margen (Margen / Earn Revenue) |  |  |  | 1% | 2% | 4% | 6% | 4% | 4% | 4% |  | 4%
Concept | Current Month (To go-1) | Current Month Real | Cumulative to date |  | To go Month 2 | To go Month 3 | To go Month 4 | To go Month 5 | Current Remaining | At completion Current | At completion Previous | At completion Target
EARN REVENUE | 132677.44 | 133160 | 133160 |  | 150493.28 | 240685.76 | 500808 | 237084.96 | 1129072 | 1262232 |  | 1261232
Earn value | 118462 | 118000 | 118000 |  | 134369 | 214898 | 447150 | 211683 | 1008100 | 1126100 |  | 1126100
Profit + overheads (12%) | 14215.44 | 14160 | 14160 |  | 16124.28 | 25787.76 | 53658 | 25401.96 | 120972 | 135132 |  | 135132
Additional Claims |  | 1000 | 1000 | [5 empty] | 0 | 1000 |  | 0
Claims to other projects | [8 empty] | 0 | 0 |  | 0
Claims to third parties | [8 empty] | 0 | 0 |  | 0
Claims to subcontractos | [8 empty] | 0 | 0 |  | 0
COST | 131095.7041 | 135440 | 135440 |  | 147144.8435 | 231303.8495 | 472640.5099 | 227963.0931 | 1079052.2959 | 1214492.2959 |  | 1210148
Materials | 98476.5633 | 97000 | 97000 |  | 41743.453 | 89321.5398 | 185856.204 | 87985.2372 | 404906.434 | 501906.434 |  | 503382.9973
Labor | 0 |  | 0 |  | 83486.9061 | 111651.9247 | 232320.255 | 109981.5465 | 537440.6323 | 537440.6323 |  | 537440.6323
Subcontractor | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Plant | 24619.1408 | 30440 | 30440 |  | 13914.4843 | 22330.3849 | 46464.051 | 21996.3093 | 104705.2296 | 135145.2296 |  | 129324.3704
Overhead and indirects | 8000 | 8000 | 8000 |  | 8000 | 8000 | 8000 | 8000 | 32000 | 40000 |  | 40000
[9 empty] | 0 | 0 |  | 0
Profit ('Earn revenue - Cost) |  | -2280 |  |  | 3348.4365 | 9381.9105 | 28167.4901 | 9121.8669 | 50019.7041 | 47739.7041 |  | 51084
%Profit (Profit / Earn Revenue) |  | -2% |  |  | 2% | 4% | 6% | 4% | 4% | 4% |  | 4%

## Cost category
Cost Category | Description
Labour
Material
Equipment

## CBSS
Code | Cost account | Description
C-100 | Cost account 1
C-200 | Cost account 2
C-300 | Cost account 3
C-400 | Cost account 4

## Budget
BUDGET
Activity | Activity title | Cantidad | Price | Cost | Duration
WBS 1 | PROVISIONALES
Activity 1 | CARTEL PARA LA OBRA DE 3.60X2.40M. | 1 | 80000 | 80000 | 15
Activity 2 | ALQUILER DE VIVIENDA PARA OFICINA Y ALMACÉN | 1 | 50000 | 50000 | 10
Activity 3 | MOVILIZACION Y DESMOVILIZACION DE EQUIPO | 1 | 50000 | 50000 | 10
WBS 2 | OBRAS PRELIMINARES |  |  |  | 20
Activity 4 | LIMPIEZA DE TERRENO MANUAL | 2400 | 14 | 33600 | 10
Activity 5 | TRAZO Y REPLANTEO INICIALES DEL PROYECTO | 6000 | 14 | 84000 | 10
WBS 3 | MOVIMIENTO DE TIERRAS |  |  |  | 50
Activity 6 | EXCAVACION MASIVA CON MAQUINA | 14000 | 12 | 168000 | 15
Activity 7 | RELLENO COMPACTADO CON MATERIAL PROPIO | 8000 | 35 | 280000 | 10
Activity 8 | RELLENO COMPACTADO CON MATERIAL DE PRESTAMO | 750 | 70 | 52500 | 15
WBS 4 | CONCRETO SIMPLE |  |  |  | 20
WBS 4.1 | SOLADO PARA ZAPATAS |  |  |  | 5
Activity 9 | SOLADO DE CONCRETO PARA ZAPATAS MEZCLA 1:12 (e=2") | 200 | 25 | 5000 | 5
WBS 4.1 | MUROS DE CONTENCION |  |  |  | 15
Activity 10 | ENCOFRADO Y DESENCOFRADO NORMAL PARA MUROS DE CONTENCION | 5000 | 45 | 225000 | 10
Activity 11 | ENCOFRADO Y DESENCOFRADO NORMAL EN ZAPATAS DE MURO | 750 | 50 | 37500 | 15
Activity 12 | CONCRETO CICLOPEO 30%PM PARA MUROS f'c=140 kg/m2 | 1100 | 55 | 60500 | 5
1126100

## Budget Cost
| BUDGET |  |  |  | Code Of Accounts |  | Cost per Unit |  |  | Cost per Unit |  |  | Cost per Quantity |  | Activity Name | Planned Start | Planned Finish | Progress |  |  |  | Cost planned due to the actual progress
Activity | Qty | Price | Cost | Code | Cost account | Unit pctg Labour | Unit pctg Mat | Unit pctg Eq. | unit cost Labour | unit cost Mat | unit cost Eq. | subtotal Labour | subtotal Mat | subtotal Eq. | Activity Name | Planned Start | Planned Finish | % | EV | Code | Labour | Mat | Eq.
WBS 1 | [14 empty] | PROVISIONALES
Activity 1 | 1 | 80000 | 80000 | C-100 | Cost account 1 | 0% | 100% | 0% | 0 | 80000 | 0 | 0 | 80000 | 0 | CARTEL PARA LA OBRA DE 3.60X2.40M. | 2026-05-06 | 2026-05-26 | 100% | 80000 | C-100 | 0 | 80000 | 0
Activity 2 | 1 | 50000 | 50000 | C-100 | Cost account 1 | 0% | 100% | 0% | 0 | 50000 | 0 | 0 | 50000 | 0 | ALQUILER DE VIVIENDA PARA OFICINA Y ALMACÉN | 2026-05-27 | 2026-06-09 | 38% | 19000 | C-100 | 0 | 19000 | 0
Activity 3 | 1 | 50000 | 50000 | C-100 | Cost account 1 | 0% | 0% | 100% | 0 | 0 | 50000 | 0 | 0 | 50000 | MOVILIZACION Y DESMOVILIZACION DE EQUIPO | 2026-05-27 | 2026-06-09 | 38% | 19000 | C-100 | 0 | 0 | 19000
WBS 2 | [8 empty] | 0 | 0 | 0 |  |  |  | OBRAS PRELIMINARES
Activity 4 | 2400 | 14 | 33600 | C-100 | Cost account 1 | 97.04% | 0% | 2.964% | 13.585 | 0 | 0.41498 | 32604.0517 | 0 | 995.9483 | LIMPIEZA DE TERRENO MANUAL | 2026-06-10 | 2026-06-23 |  | 0 | C-100 | 0 | 0 | 0
Activity 5 | 6000 | 14 | 84000 | C-100 | Cost account 1 | 36.51% | 57.14% | 6.349% | 5.1111 | 8 | 0.88891 | 30666.7198 | 47999.8405 | 5333.4396 | TRAZO Y REPLANTEO INICIALES DEL PROYECTO | 2026-06-24 | 2026-07-07 |  | 0 | C-100 | 0 | 0 | 0
WBS 3 | [14 empty] | MOVIMIENTO DE TIERRAS | 2026-07-08 | 2026-09-15
Activity 6 | 14000 | 12 | 168000 | C-200 | Cost account 2 | 39.68% | 0% | 60.32% | 4.7611 | 0 | 7.2389 | 66655.8327 | 0 | 101344.1673 | EXCAVACION MASIVA CON MAQUINA | 2026-07-08 | 2026-07-28 |  | 0 | C-200 | 0 | 0 | 0
Activity 7 | 8000 | 35 | 280000 | C-200 | Cost account 2 | 75.43% | 1.129% | 23.44% | 26.3993 | 0.39512 | 8.2056 | 211194.5174 | 3160.9261 | 65644.5565 | RELLENO COMPACTADO CON MATERIAL PROPIO | 2026-08-26 | 2026-09-08 |  | 0 | C-200 | 0 | 0 | 0
Activity 8 | 750 | 70 | 52500 | C-200 | Cost account 2 | 41.86% | 45.13% | 13.01% | 29.2992 | 31.5939 | 9.107 | 21974.3844 | 23695.3966 | 6830.219 | RELLENO COMPACTADO CON MATERIAL DE PRESTAMO | 2026-08-26 | 2026-09-15 |  | 0 | C-200 | 0 | 0 | 0
WBS 4 | [8 empty] | 0 | 0 | 0 |  |  |  | CONCRETO SIMPLE
WBS 4.1 | [14 empty] | SOLADO PARA ZAPATAS
Activity 9 | 200 | 25 | 5000 | C-300 | Cost account 3 | 61.15% | 31.21% | 7.639% | 15.2874 | 7.8029 | 1.9097 | 3057.4846 | 1560.571 | 381.9444 | SOLADO DE CONCRETO PARA ZAPATAS MEZCLA 1:12 (e=2") | 2026-07-29 | 2026-08-04 |  | 0 | C-300 | 0 | 0 | 0
WBS 4.2 | [8 empty] | 0 | 0 | 0 |  |  |  | MUROS DE CONTENCION
Activity 10 | 5000 | 45 | 225000 | C-400 | Cost account 4 | 50.89% | 47.58% | 1.527% | 22.9008 | 21.4122 | 0.68703 | 114503.7978 | 107061.0476 | 3435.1546 | ENCOFRADO Y DESENCOFRADO NORMAL PARA MUROS DE CONTENCION | 2026-08-05 | 2026-08-18 |  | 0 | C-400 | 0 | 0 | 0
Activity 11 | 750 | 50 | 37500 | C-400 | Cost account 4 | 55.44% | 42.9% | 1.664% | 27.7184 | 21.4497 | 0.83191 | 20788.7631 | 16087.3077 | 623.9293 | ENCOFRADO Y DESENCOFRADO NORMAL EN ZAPATAS DE MURO | 2026-08-05 | 2026-08-11 |  | 0 | C-400 | 0 | 0 | 0
Activity 12 | 1100 | 55 | 60500 | C-300 | Cost account 3 | 52.11% | 42.88% | 5.008% | 28.6592 | 23.5864 | 2.7544 | 31525.1541 | 25945.0495 | 3029.7964 | CONCRETO CICLOPEO 30%PM PARA MUROS f'c=140 kg/m2 | 2026-08-19 | 2026-08-25 |  | 0 | C-300 | 0 | 0 | 0
|  |  | 1126100 | [8 empty] | 532970.7056 | 355510.1389 | 237619.1554 | 1126100 |  |  |  | 118000 |  | 0 | 99000 | 19000

## Estructura de Control
Code CA | LABOUR C | MATERIAL C | EQUIPMENT C
C-100 | 492 | 2490 | 498
C-200 | 12465 | 14825 | 9460
C-300 | 1674 | 1570 | 3306
C-400 | 7500 | 11125 | 7625
Total general | 22131 | 30010 | 20889 | 73030
Code CA | Suma de Labour | Suma de Mat | Suma de Eq.
C-100 | 246 | 2145 | 249 | [10 empty] | Code CA | Category | EV | AC | CV | Profit
C-200 | 3116.25 | 3706.25 | 2365 | [10 empty] | C-100 | Labour | 246 | 150 | 96
C-300 | 424.5 | 400 | 938 | [10 empty] | C-200 | Labour | 3116.25 | 2500 | 616.25
C-400 | 1875 | 2781.25 | 1906.25 | [10 empty] | C-300 | Labour | 424.5 | 400 | 24.5
Total general | 5661.75 | 9032.5 | 5458.25 | [10 empty] | C-400 | Labour | 1875 | 2500 | -625
[14 empty] | C-100 | Material | 2145 | 1500 | 645
[14 empty] | C-200 | Material | 3706.25 | 4500 | -793.75
[14 empty] | C-300 | Material | 400 | 1000 | -600
[14 empty] | C-400 | Material | 2781.25 | 3500 | -718.75
[14 empty] | C-100 | Equipment | 249 | 200 | 49
[14 empty] | C-200 | Equipment | 2365 | 2400 | -35
[14 empty] | C-300 | Equipment | 938 | 900 | 38
[14 empty] | C-400 | Equipment | 1906.25 | 2300 | -393.75
[14 empty] | Subtotal |  | 20152.5 | 21850 | -1697.5
[14 empty] | Overhead |  | 2015.25 | 2185
[14 empty] | Subtotal 2 |  | 22167.75 | 24035
[14 empty] | Another concepts to claim |  | 3500
| EV |  |  |  |  | AC |  |  |  | GAP |  |  |  | Total |  | 25667.75 | 24035 | 1632.75 | 6.361%
Code CA | Labour | Material | Equipment | Subtotal 1 | Code CA | Labour | Material | Equipment | Subtotal 2 | Labour | Material | Equipment | Subtotal 2
C-100 | 246 | 2145 | 249 | 2640 | C-100 | 150 | 1500 | 200 | 1850 | 96 | 645 | 49 | 790
C-200 | 3116.25 | 3706.25 | 2365 | 9187.5 | C-200 | 2500 | 4500 | 2400 | 9400 | 616.25 | -793.75 | -35 | -212.5
C-300 | 424.5 | 400 | 938 | 1762.5 | C-300 | 400 | 1000 | 900 | 2300 | 24.5 | -600 | 38 | -537.5
C-400 | 1875 | 2781.25 | 1906.25 | 6562.5 | C-400 | 2500 | 3500 | 2300 | 8300 | -625 | -718.75 | -393.75 | -1737.5
| 5661.75 | 9032.5 | 5458.25 | 20152.5 |  | 5550 | 10500 | 5800 | 21850 | 111.75 | -1467.5 | -341.75 | -1697.5
Code CA | Description CA | Support Gap | Actions to implement
C-100 | Cost account 1 | Explanation one | Actions to implement one.
C-200 | Cost account 2 | Explanation two | Actions to implement two.
C-300 | Cost account 3 | Explanation three | Actions to implement three.
C-400 | Cost account 4 | Explanation four | Actions to implement four.

## CV reconciliation
Valuation | 25850
Request for payment | 20000 | 111730.65
Accruals | 3500 | 5000
Cost | Budgeted Cost | Actual Cost | Gap
Labour | 5661.75 | 5550 | 111.75
Material | 9032.5 | 10500 | -1467.5
Equipment | 5458.25 | 5800 | -341.75
GG =0.1*CD | 2015.25 | 2185 | -169.75
SUB TOTAL | 22167.75 | 24035 | -1867.25
| Profit | 1815
| Profit | 7.021%
| EV' | 25850
| AC | 24035
| CPI | 1.0755

## Budgett
Code | Suma de Cost
C-100 | 3480
C-200 | 36750
C-300 | 6550
C-400 | 26250
(en blanco)
Total general | 73030

## P6
WBS | Activity ID | Activity Name | Planned Start | Planned Finish | COA | Original Duration | Budget
RO_01 RO_Sample |  |  | 2026-05-06 | 2026-09-15 |  | 95
RO_01.1 WBS 1 |  |  | 2026-05-06 | 2026-06-09 |  | 25
RO_01.1 | A1000 | Activity 1 | 2026-05-06 | 2026-05-26 | Cost account 1 | 15 | 80000
RO_01.1 | A1010 | Activity 2 | 2026-05-27 | 2026-06-09 | Cost account 1 | 10 | 50000
RO_01.1 | A1020 | Activity 3 | 2026-05-27 | 2026-06-09 | Cost account 1 | 10 | 50000
RO_01.2 WBS 2 |  |  | 2026-06-10 | 2026-07-07 |  | 20
RO_01.2 | A1030 | Activity 4 | 2026-06-10 | 2026-06-23 | Cost account 1 | 10 | 33600
RO_01.2 | A1040 | Activity 5 | 2026-06-24 | 2026-07-07 | Cost account 1 | 10 | 84000
RO_01.3 WBS 3 |  |  | 2026-07-08 | 2026-09-15 |  | 50
RO_01.3 | A1050 | Activity 6 | 2026-07-08 | 2026-07-28 | Cost account 2 | 15 | 168000
RO_01.3 | A1060 | Activity 7 | 2026-08-26 | 2026-09-08 | Cost account 2 | 10 | 280000
RO_01.3 | A1070 | Activity 8 | 2026-08-26 | 2026-09-15 | Cost account 2 | 15 | 52500
RO_01.4 WBS4 |  |  | 2026-07-29 | 2026-08-25 |  | 20
RO_01.4.1 WBS 4.1 |  |  | 2026-07-29 | 2026-08-04 |  | 5
RO_01.4.1 | A1080 | Activity 9 | 2026-07-29 | 2026-08-04 | Cost account 3 | 5 | 5000
RO_01.4.2 WBS 4. 2 |  |  | 2026-08-05 | 2026-08-25 |  | 15
RO_01.4.2 | A1090 | Activity 10 | 2026-08-05 | 2026-08-18 | Cost account 4 | 10 | 225000
RO_01.4.2 | A1100 | Activity 11 | 2026-08-05 | 2026-08-11 | Cost account 4 | 5 | 37500
RO_01.4.2 | A1110 | Activity 12 | 2026-08-19 | 2026-08-25 | Cost account 3 | 5 | 60500

## Activtiy Progress
Cost account | Activity | Unit | Quantity | Budget | Start | Finish | Actual qty | EV | EV (Cost account) | AC | ETC | EAC
Cost account 1 | [8 empty] | 118000 | 127440 | 179088 | 306528
Cost account 1 | Activity 1 | % | 100% | 80000 | 2026-05-06 | 2026-05-26 | 100% | 80000
Cost account 1 | Activity 2 | % | 100% | 50000 | 2026-05-27 | 2026-06-09 | 38% | 19000
Cost account 1 | Activity 3 | % | 100% | 50000 | 2026-05-27 | 2026-06-09 | 38% | 19000
Cost account 1 | Activity 4 | m2 | 2400 | 33600 | 2026-06-10 | 2026-06-23
Cost account 1 | Activity 5 | m2 | 6000 | 84000 | 2026-06-24 | 2026-07-07
Cost account 2 | [8 empty] | 0 | 0 | 520520 | 520520
Cost account 2 | Activity 6 | m3 | 14000 | 168000 | 2026-07-08 | 2026-07-28
Cost account 2 | Activity 7 | m3 | 8000 | 280000 | 2026-08-26 | 2026-09-08
Cost account 2 | Activity 8 | m3 | 750 | 52500 | 2026-08-26 | 2026-09-15
Cost account 3 | [8 empty] | 0 | 0 | 70100 | 70100
Cost account 3 | Activity 12 | m3 | 1100 | 60500 | 2026-08-19 | 2026-08-25
Cost account 3 | Activity 9 | m2 | 200 | 5000 | 2026-07-29 | 2026-08-04
Cost account 4 | [8 empty] | 0 | 0 | 273000 | 273000
Cost account 4 | Activity 10 | m2 | 5000 | 225000 | 2026-08-05 | 2026-08-18
Cost account 4 | Activity 11 | m3 | 750 | 37500 | 2026-08-05 | 2026-08-11

## Activtiy Progress_2
Cost account | Activity | Unit | Quantity | Budget | Start | Finish | Actual qty | EV | EV (Cost account) | AC | ETC | EAC
Cost account 1 | [8 empty] | 222000 | 239760 | 66768 | 306528
Cost account 1 | Activity 1 | % | 100% | 80000 | 2026-05-06 | 2026-05-26 | 100% | 80000
Cost account 1 | Activity 2 | % | 100% | 50000 | 2026-05-27 | 2026-06-09 | 100% | 50000
Cost account 1 | Activity 3 | % | 100% | 50000 | 2026-05-27 | 2026-06-09 | 100% | 50000
Cost account 1 | Activity 4 | m2 | 2400 | 33600 | 2026-06-10 | 2026-06-23 | 100% | 33600
Cost account 1 | Activity 5 | m2 | 6000 | 84000 | 2026-06-24 | 2026-07-07 | 10% | 8400
Cost account 2 | [8 empty] | 0 | 0 | 520520 | 520520
Cost account 2 | Activity 6 | m3 | 14000 | 168000 | 2026-07-08 | 2026-07-28
Cost account 2 | Activity 7 | m3 | 8000 | 280000 | 2026-08-26 | 2026-09-08
Cost account 2 | Activity 8 | m3 | 750 | 52500 | 2026-08-26 | 2026-09-15
Cost account 3 | [8 empty] | 0 | 0 | 70100 | 70100
Cost account 3 | Activity 12 | m3 | 1100 | 60500 | 2026-08-19 | 2026-08-25
Cost account 3 | Activity 9 | m2 | 200 | 5000 | 2026-07-29 | 2026-08-04
Cost account 4 | [8 empty] | 0 | 0 | 273000 | 273000
Cost account 4 | Activity 10 | m2 | 5000 | 225000 | 2026-08-05 | 2026-08-18
Cost account 4 | Activity 11 | m3 | 750 | 37500 | 2026-08-05 | 2026-08-11

## EVM
Period | Variable | Value |  | Period | EV | AC | PV | PV cum
2026-01-05 | EV | 118000 |  | may-26 | 118000 | 127440 | 118462 | 118462
2026-01-05 | AC | 127440 |  | jun-26 |  |  | 133907 | 252369
2026-01-05 | PV | 118462 |  | jul-26 |  |  | 214898 | 467267
2026-01-06 | PV | 133907 |  | aug-26 |  |  | 447150 | 914417
2026-01-07 | PV | 214898 |  | sep-26 |  |  | 211683 | 1126100
2026-01-08 | PV | 447150
2026-01-09 | PV | 211683
|  |  | CA | CA2 | EV | AC | PV | CV | SV | CPI | SPI
|  |  | C-100 | Cost account 1 | 118000 | 127440 | 118462 | -9440 | -462 | 0.92593 | 0.9961
|  |  | C-200 | Cost account 2
|  |  | C-300 | Cost account 3
|  |  | C-400 | Cost account 4

## EAC
Cost account 3
Resource name | Type | Unit | Qty to date | Unit rate TD | Cost to date | Qty to Complete | Unit rate TC | Cost to compelte
Resource 1 | Labor | HH | 0 |  | 0 | 50 | 180 | 9000
Resource 2 | Labor | HH | 0 |  | 0 | 50 | 185 | 9250
Resource 3 | Labor | HH | 0 |  | 0 | 50 | 185 | 9250
Resource 4 | Material | m3 | 0 |  | 0 | 370 | 65 | 24050
Resource 5 | Material | m2 | 0 |  | 0 | 380 | 20 | 7600
Resource 6 | Material | ea | 0 |  | 0 | 60 | 2.5 | 150
Resource 7 | Material | ea | 0 |  | 0 | 50 | 2.5 | 125
Resource 8 | Material | ea | 0 |  | 0 | 50 | 3.5 | 175
Resource 9 | Plant | Day | 0 |  | 0 | 5 | 1500 | 7500
Resource 10 | Plant | Day | 0 |  | 0 | 2 | 1500 | 3000
[5 empty] | 0 |  |  | 70100